## Slide 1
INVESTEC
August Learnership Progress Report
National Certificate: Information Technology - Systems Support • August 2026
SAQA ID
48573
Sponsor
Investec Group
NQF level
Level 5 • 148 credits
Reporting period
1–31 August 2026
Facilitator
Andre Snell
Cohort
12 learners
HR MANAGEMENT VIEW
Attendance, delivery, assessment progress and learner engagement
A clear view of achievement, current activity and the focused support that will sustain momentum.
Eruditio • Empower · Develop · Transform
01
Notes: Slide 1: present the verified August position using positive, phase-aware language.
[Sources]
- Learner-Tracker-Investec-Aug-2026 (1).html — statuses, learner observations and attendance matrix as at 13 August 2026
- Attendance Register INVESTEC.pdf — signed registers supporting the earlier contact-session record
- Learnership-Progress-Report-Investec-Aug-2026.pdf — earlier delivery, assessment and learner-progress position
- Register28August2026 Investec.pdf — 12 of 12 learners attended US 114051 training on 28 August 2026

## Slide 2
INVESTEC • AUGUST LEARNERSHIP REPORT
The programme maintained strong attendance through month-end
12
Learners enrolled
Full programme complement
100%
Recorded attendance
Across four August sessions
95%
First knowledge quiz
Cohort average
11/12
At or above 80%
Across marked activity to date
HR EXECUTIVE POSITION
Learner work is complete and marked; assessor finalisation is now in progress.
Completed Unit Standard activities and quizzes are marked and stored on the LMS. On 28 August, all 12 learners attended the US 114051 training session. “In Progress” may remain while the assessor completes logbook marking, submission review and documentation.
Eruditio • Empower · Develop · Transform
02
Notes: Slide 2: present the verified August position using positive, phase-aware language.
[Sources]
- Learner-Tracker-Investec-Aug-2026 (1).html — statuses, learner observations and attendance matrix as at 13 August 2026
- Attendance Register INVESTEC.pdf — signed registers supporting the earlier contact-session record
- Learnership-Progress-Report-Investec-Aug-2026.pdf — earlier delivery, assessment and learner-progress position
- Register28August2026 Investec.pdf — 12 of 12 learners attended US 114051 training on 28 August 2026

## Slide 3
INVESTEC • AUGUST LEARNERSHIP REPORT
Attendance demonstrates exceptional learner commitment
SIGNED ATTENDANCE BY CONTACT SESSION
5 August
12 / 12
6 August
12 / 12
7 August
12 / 12
28 August
12 / 12
August total
48 / 48
100%
recorded attendance
Signed registers
Four August sessions on file
All four August contact sessions were fully attended. The 28 August register confirms 12 of 12 learners present for US 114051, sustaining 100% recorded attendance for the month.
Eruditio • Empower · Develop · Transform
03
Notes: Slide 3: present the verified August position using positive, phase-aware language.
[Sources]
- Learner-Tracker-Investec-Aug-2026 (1).html — statuses, learner observations and attendance matrix as at 13 August 2026
- Attendance Register INVESTEC.pdf — signed registers supporting the earlier contact-session record
- Learnership-Progress-Report-Investec-Aug-2026.pdf — earlier delivery, assessment and learner-progress position
- Register28August2026 Investec.pdf — 12 of 12 learners attended US 114051 training on 28 August 2026

## Slide 4
INVESTEC • AUGUST LEARNERSHIP REPORT
Delivery remained on schedule through month-end
CURRICULUM PROGRESSION
Completed delivery
Next standard scheduled
Completed work is marked on the LMS; US 114051 training was delivered on 28 August.
Delivery point
Timing
Learning position
Evidence position
HR view
US 8252
17 July
Learner work complete
Marked & stored on LMS
Assessor finalisation
US 10135
24 Jul & 7 Aug
Learner work complete
Marked & stored on LMS
Assessor finalisation
US 114051
28 August
Training delivered
Register on file
12 / 12 attended
Month-end delivery is confirmed: US 114051 was delivered on 28 August with 12 of 12 learners present; US 114046 is scheduled for early September.
Eruditio • Empower · Develop · Transform
04
Notes: Slide 4: present the verified August position using positive, phase-aware language.
[Sources]
- Learner-Tracker-Investec-Aug-2026 (1).html — statuses, learner observations and attendance matrix as at 13 August 2026
- Attendance Register INVESTEC.pdf — signed registers supporting the earlier contact-session record
- Learnership-Progress-Report-Investec-Aug-2026.pdf — earlier delivery, assessment and learner-progress position
- Register28August2026 Investec.pdf — 12 of 12 learners attended US 114051 training on 28 August 2026

## Slide 5
INVESTEC • AUGUST LEARNERSHIP REPORT
Early results show strong competence and momentum
Measure
Performance indicator
Value
First quiz
Cohort average
95%
Both standards
Average marked activity
92%
Threshold
Learners at / above 80%
11/12
Mastery
Perfect quiz scores
6
Quiz result
Below 80%
0
Retry practice
Average formative attempts
2.8
Measure
Performance indicator
Value
US10135 Q1
Teamwork & autonomy mean
91.3
US10135 Q2
Coherence & respect mean
91.1
US10135 Q3
Stakeholder relations mean
84.8
Platform
Active within last 24 hours
50%
Attend.
Facilitated sessions
100%
Cohort
Full programme complement
12
11 OF 12 LEARNERS CURRENTLY AT OR ABOVE THE 80% THRESHOLD
92%
Eruditio • Empower · Develop · Transform
05
Notes: Slide 5: present the verified August position using positive, phase-aware language.
[Sources]
- Learner-Tracker-Investec-Aug-2026 (1).html — statuses, learner observations and attendance matrix as at 13 August 2026
- Attendance Register INVESTEC.pdf — signed registers supporting the earlier contact-session record
- Learnership-Progress-Report-Investec-Aug-2026.pdf — earlier delivery, assessment and learner-progress position
- Register28August2026 Investec.pdf — 12 of 12 learners attended US 114051 training on 28 August 2026

## Slide 6
INVESTEC • AUGUST LEARNERSHIP REPORT
Evidence is moving through the planned assessment pathway
EVIDENCE AND SUBMISSION READINESS
Activities & quizzes complete
Assessor finalisation follows
“In Progress” reflects pending assessor review and documentation—not incomplete learner work.
Evidence stream
Learners
Current achievement
Next evidence step
Position
US 8252
12 / 12
Learner work complete
Logbook & submission review
Finalisation pending
US 10135
12
Learner work complete
Logbook & submission review
Finalisation pending
US 114051
12 / 12
Training attended
Learner evidence follows
Delivery complete
Completed Unit Standard work remains in assessor finalisation. US 114051 training attendance is recorded for all 12 learners, with learner evidence to follow the planned pathway.
Eruditio • Empower · Develop · Transform
06
Notes: Slide 6: present the verified August position using positive, phase-aware language.
[Sources]
- Learner-Tracker-Investec-Aug-2026 (1).html — statuses, learner observations and attendance matrix as at 13 August 2026
- Attendance Register INVESTEC.pdf — signed registers supporting the earlier contact-session record
- Learnership-Progress-Report-Investec-Aug-2026.pdf — earlier delivery, assessment and learner-progress position
- Register28August2026 Investec.pdf — 12 of 12 learners attended US 114051 training on 28 August 2026

## Slide 7
INVESTEC • AUGUST LEARNERSHIP REPORT
The cohort is engaged, collaborative and ready to grow
01
Positive learning culture
Learners participate enthusiastically, ask questions freely and support one another in class.
02
Technical curiosity
The group shows strong interest in IT, hardware and applying technical knowledge in practical contexts.
03
Self-directed effort
Six learners accessed the platform within 24 hours, demonstrating study activity beyond contact sessions.
04
Cohort continuity
The replacement learner was onboarded promptly, is attending and has structured catch-up support in place.
COHORT POSITION: committed attendance, encouraging results and a strong platform for continued development
Eruditio • Empower · Develop · Transform
07
Notes: Slide 7: present the verified August position using positive, phase-aware language.
[Sources]
- Learner-Tracker-Investec-Aug-2026 (1).html — statuses, learner observations and attendance matrix as at 13 August 2026
- Attendance Register INVESTEC.pdf — signed registers supporting the earlier contact-session record
- Learnership-Progress-Report-Investec-Aug-2026.pdf — earlier delivery, assessment and learner-progress position
- Register28August2026 Investec.pdf — 12 of 12 learners attended US 114051 training on 28 August 2026

## Slide 8
INVESTEC • AUGUST LEARNERSHIP REPORT
A focused three-month investment will protect momentum
01
Approve targeted contact time
Increase delivery to six contact days per month for the next three months.
02
Complete assessor finalisation
Complete logbook marking, submission review and the required documentation.
03
Build platform confidence
Reinforce submission, progress tracking and independent study habits during contact time.
04
Return to standard rhythm
Resume four contact days per month once independent learning habits are established.
PROPOSED SUPPORT MODEL
3
months of targeted support
2
additional days per month
4
days per month thereafter
100%
recorded attendance
Recommendation: approve six contact days per month for three months
Eruditio • Empower · Develop · Transform
08
Notes: Slide 8: present the verified August position using positive, phase-aware language.
[Sources]
- Learner-Tracker-Investec-Aug-2026 (1).html — statuses, learner observations and attendance matrix as at 13 August 2026
- Attendance Register INVESTEC.pdf — signed registers supporting the earlier contact-session record
- Learnership-Progress-Report-Investec-Aug-2026.pdf — earlier delivery, assessment and learner-progress position
- Register28August2026 Investec.pdf — 12 of 12 learners attended US 114051 training on 28 August 2026